## Sheet1
SUSTAINABILITY PROJECTS FUND Impact Metric
Project Name: Constructive Consumerism
Project Number: SP0080
Project Leader: Courtney Quinn
Accountable Person: Courtney Quinn
Date Submitted: November 24, 2013
*Note that metrics/targets were altered in actual realization of project
Indicator (qualitative or quantitative) | Target | End of Project Target Status
Academics
Number of Environment Students recieveing credit | 4 | 0
Number of management students recieveing credit | 2 | 2 - decided that just mgmt students w/ envr coordinator due to administrative purposes
Number of theses or papers addedd to MFSP database | 4 | 1 ASR report, 1 final report, and ASR supplemtal materials
All Projects
Number of Partners | 4 | 4 (MFSP, MIIDM management, MOoS, SHHS)
Number of McGill Faculties involved | Management - 1 | 1, management. MSE involved indirectly through MFSP support
Number of people employed | 1 | 1
Number of participants | 6 | 2 - students that participated in ASR
Project completed by project deadline | Fall 2013 | ASR completed Fall 2014, project wrap up beginning of winter 2015 with follow-up Winter 2015
New project deadline | Fall 2014 at latest
Chance that project will continue after funding is gone | Yes, to be instiutionalized in management faculty | Have established good relations with Admin and new managing for sustainability major coordinator, and we hope more MFSP/Management faculty ASR projects will be realized in the future
Community
Number of projects created | 2 - implementation and follow up of marketing techniques | First project complete, now working on continuing ASR projects with managament students
Number of inquiries about the project | 5 | Inquiries to use marketing students for Sustainability app project
Food
Increase sale of organic | 5-10% | Advertising schemes for local food days saw an increase in attendence in Novemeber by 56% from October and 36% from September. In-person surveys indicated at that 20% of students attended local food day due to facebook advertising and 71% had seen the TV advertising.
Increase sale of local food | 5-10%
Increase sale of Vegan/Vegetarian option | 5-10%
Long-term Instiutionalization Metrics
Number of MFSP ASR projects with Management students | 1-2 per year | Currently in the process of trying to set up more ASR projects with management faculty to not loose out on the opportunity of having awarenss and some support from Management admin. Nothing is set up thus far, but this is an idea for how the rest of the funding could be used. It is too early to give an exact number.
Number of colloborative projects with MDIIM | 1 per year
Number of cross-faculty ASR projects | 1 per year
Inclusion of Arts students in ASR projects | 2 | Creating an Arts faculty ASR code was sonething that was discuessed before I went on exchange in Winter of 2014, but I heard very little information about when I returned in Fall of 2014. This may be because key people pushing for this had left. I've still included this in my recommendations in the final report, but realistically I think it will take a few years to see this institutionalized.